## website
No | Tasks | Sub tasks | Progress |  | Remarks
|  |  | UI | Function
1 | Home page | Home page | done | - | using ent api
|  | responseive design | done | -
|  | redirect to video page | - | done
2 | Video page | Video page | done | - | using ent api
|  | video player | done | autoplay is ok, ima is not done
|  | responseive design | done | -
|  | emoji comment section | done | not done
|  | emoji box | done | -
|  | share box | done | not done
|  | facebook share | - | not done
|  | word size | done | done
|  | text comment section | done | not done
3 | Category page | Category page | not done | -
|  | responseive design | not done | -
4 | header | login | done | not done
|  | full menu | done | -
|  | mobile menu | done | done (redirect to pages)
|  | search box | done | not done
|  | navbar | done | done | using ent api
5 | footer | footer
6 | video page header | scroll down change content | not done | -
|  | responseive design | not done | -
|  | moblle menu | working now | -
7 | video page footer | footer | done | -
8 | search page | search page | not done | -
|  | responseive design | not done | -
9 | tag list page | tag list page | not done | -
|  | responseive design | not done | -
10 | live page | live page | not done | -
|  | video player | not done | not done
|  | responseive design | not done | -

## app
No | Tasks | Sub tasks | Progress |  | Remarks
|  |  | UI | Function
1 | formatting code |  | - | always in progress
2 | theme | light | done | -
|  | dark | working | -
3 | live video | auto scroll to current channel | working | working
4 | login | login | done | not working